## Sheet1
Tasks to be Completed |  | DAYS
Task Name | Subtasks | Days 1-20 | Days 21-50 | Days 51-70 | Days 71-120 | Days 121-130 | Days 131-150
Introduction | Overview
Background Study
Aim and Objectives
Resesearch Questions
| Finalize and Document | 15%
Literature Review | Draft
Complete
Comparison
| Finalize and Document |  | 40%
Methodology | Framing Approach for Research
Description of Methodology Steps
Prefernce of Tool
Selection of Data
Selection of Classifiers (Machine Learning and Deep Learning)
Selection of Evaluation Matrices
| Documentation |  |  | 55%
Result and Analysis | Analysis of Datasets
Data Preprocessing
Prepare data with Hybrid Features Selection with Chi-Squared and RFE
Prepare Models by tuning Hyperparameters
Apply Models to detect DDoS attacks
Detect the Best-Performing model with the highest accuracy and least overfit
Identify the improvement
| Documentation |  |  |  | 75%
Discussion and Conclusion | Addressing Research Questions
Research Limitations and Future Scopes
Advantages of Research
| Finalize and Document |  |  |  |  | 95%
Finalize Document | Submission | [5 empty] | 100%